## Sheet1
Responsibilities Chart for the ITWS Term Project
Note: We reserve the ability to add further entries as we continue to learn and work on the project.
Task: | Due Date: | Involved: | Done?
Planning
Establish who is responsible for what in Updated Term Project Proposal. | 31, Oct. 2019 | Jacob, Anthony, and Tyler | Y
Write out a website information architecture document. | 1, Dec. 2019 | Jacob, Anthony, and Tyler | Y
Establish both aesthetic and consistency standards for the site. | 6, Nov. 2019 | Jacob, Anthony, and Tyler
Project-Wide
Establish the GIT Repository. Get everybody connected to it. | 1, Nov. 2019 | Jacob | Y
Finish the Project. | 26, Nov. 2019 | Jacob, Anthony, and Tyler
HTML
Establish the base format of the website. Results in HTML template. | 6, Nov. 2019 | Tyler and Jacob
Create the Landing Page's HTML. | 8, Nov. 2019 | Tyler
Create the Registration Page's HTML. | 13, Nov. 2019 | Tyler and Anthony
Create the Login Page's HTML. | 13, Nov. 2019 | Tyler and Anthony
Create the Profile Page's HTML. | 13, Nov. 2019 | Tyler and Jacob
Create the Jam Page's HTML. | 20, Nov. 2019 | Tyler and Jacob
Create the Jam Lineup Page's HTML. | 20, Nov. 2019 | Tyler and Jacob
CSS
Establish the website's general CSS. | 8, Nov. 2019 | Anthony and Tyler
Establish the Sign In and Registration Page's CSS. | 20, Nov. 2019 | Anthony
Establish the general CSS for a Jam page. | 23, Nov. 2019 | Anthony
Establish the Jam Lineup's CSS. | 23, Nov. 2019 | Anthony and Tyler
JavaScript
Write the base_format script to load in the base elements of the website. | 10, Nov. 2019 | Jacob
Write the base_user_format script to add user-specific content to the site. | 15, Nov. 2019 | Jacob
Write the user_profile_format script to load a user on the profile page. | 15, Nov. 2019 | Jacob
Write the jam_page_format script to load a jam on the jam page. | 23, Nov. 2019 | Jacob
Write needed scripts for element animation and CSS manipulation. | 23, Nov. 2019 | Anthony and Jacob
Write basic entry-fill validation scripts for Login and Registration. | 20, Nov. 2019 | Jacob
Resources
Draw up a logo to be used for the site. (Vector Graphics) | 20, Nov. 2019 | Jacob
If need be, draw up a pattern for the sidebar. | 20, Nov. 2019 | Jacob